GOVERNMENT OF INDIA

Ministry of Health & Family Welfare · Directorate General of Health Services

Central Drugs Standard Control Organization (CDSCO)

DIGITAL DRUGS REGULATORY SYSTEM (DDRS)

Data Migration Plan

Migrating Existing CDSCO Portals to the DDRS Portal

Document Version 1.0

Date: 31 May 2026

# Table of Contents

Right-click and "Update Field" to build the Table of Contents.

# 1. Introduction

## 1.1 Purpose

This document defines the strategy, methodology, mapping, governance and acceptance approach for migrating data from the existing CDSCO portals into the new Digital Drugs Regulatory System (DDRS). It ensures accuracy, completeness and integrity of migrated data while minimising downtime and disruption to ongoing regulatory activities.

## 1.2 Scope

Identification, extraction, cleansing, transformation, loading, validation and reconciliation of legacy data.

Source systems: SUGAM, MD Online, SUGAM LABS, ONDLS and State portals.

Master data (entities, products, technical persons, labs), transactional data (applications, licences, certificates), and documents.

Incremental, phased migration aligned to the DDRS rollout.

## 1.3 Objectives & Principles

Zero data loss and full traceability (every source record accounted for).

Cleansed, de-duplicated, standardised data in DDRS.

Reversible (rollback) and reconciled at each wave.

Minimal downtime via parallel run and phased cutover.

Security and confidentiality of sensitive data throughout.

# 2. Source Systems Inventory

The legacy estate comprises the following CDSCO and State systems. Exact volumes and schemas are confirmed during the assessment phase with each system owner.

| Source System | Primary Content | Typical Formats | Target DDRS Area |
| --- | --- | --- | --- |
| SUGAM (cdscoonline.gov.in) | Central licensing/permissions, registrations, CT | RDBMS, PDF, scans | applications, licensing, clinical-trials |
| MD Online (cdscomdonline.gov.in) | Medical device & IVD manufacturing/import licences | RDBMS, PDF | applications, licensing, products |
| SUGAM LABS (sugamlabs.gov.in) | Central lab LIMS: samples, tests, reports | RDBMS, instrument files | laboratory (samples, reports, BRC) |
| ONDLS (statedrugs.gov.in) | State sales/manufacturing licences, COPP/GMP/MSC | RDBMS, PDF | applications, licensing, registry |
| State portals (various) | State-specific licences & registrations | RDBMS/CSV/XLS | applications, registry, licensing |
| Documents & scans | Supporting documents across portals | PDF/JPEG/TIFF | documents (with checksum/version) |

Reference data volume: existing portal utilisation is approximately 24.3 TB (as of March 2026), dominated by uploaded documents and scanned artefacts.

# 3. Migration Strategy

## 3.1 Approach

Migration is incremental and wave-based, synchronised with the DDRS state-rollout plan. Each wave migrates a coherent slice (a portal/State and its dependent data) into a staging area, validates and reconciles it, then promotes it to production. A parallel-run window allows verification against the legacy system before cutover.

Figure — DDRS data-migration pipeline.

## 3.2 Migration Types

| Type | Use |
| --- | --- |
| Big-bang (per slice) | Small, self-contained reference datasets |
| Phased / incremental | Primary approach — by portal/State and entity group |
| Parallel run | Critical transactional data verified against legacy before cutover |
| Delta / catch-up | Capture records created in legacy during the migration window |

# 4. Migration Methodology

### 4.1 Assessment & Profiling

Inventory sources, profile data quality, define scope, volumes and risks per system.

### 4.2 Extraction

Extract from source RDBMS/exports (API/DB/CSV); land in a secure staging area.

### 4.3 Cleansing & De-duplication

Standardise formats, fix anomalies, de-duplicate entities/products, resolve orphan references.

### 4.4 Transformation & Mapping

Map source schemas to DDRS entities/fields; derive reference numbers; normalise enums.

### 4.5 Loading

Bulk-load into DDRS via repositories/ETL with referential integrity and batching.

### 4.6 Validation

Row counts, checksums, business-rule and referential checks; sample audits.

### 4.7 Reconciliation

Reconcile source vs target per entity; sign-off; record exceptions.

### 4.8 Cutover & Hypercare

Switch users to DDRS; monitor; apply deltas; support.

# 5. Data Mapping (Source → DDRS)

## 5.1 Entity-Level Mapping

| Legacy Concept | Source | DDRS Entity | Notes |
| --- | --- | --- | --- |
| Firm / Company | SUGAM/ONDLS/MD | organizations | De-dup by PAN/GSTIN/CIN |
| Product / Brand | SUGAM/MD | products | Brand-name de-duplication applied |
| Technical/competent person | ONDLS/SUGAM | technical_persons | Enforce one-entity engagement |
| Testing laboratory | SUGAM LABS/ONDLS | laboratories | Central/State/Private typing |
| Application / permission | SUGAM/MD/ONDLS | applications (+events) | Map status to DDRS state machine |
| Licence / permission grant | SUGAM/MD/ONDLS | licenses | Preserve number; regenerate QR |
| Certificate / NOC (COPP/FSC/MSC/NCC) | SUGAM/ONDLS | certificates | Map certType; set validity |
| Sample / test report | SUGAM LABS | samples, test_reports | Map result to SQ/NSQ/Spurious |
| Clinical trial | SUGAM | clinical_trials (+sites) | Link CTRI / EC approvals |
| Payment / challan | SUGAM/ONDLS | payments | Status PAID; map gateway |
| Uploaded document | All | documents | Store ref + checksum + version |

## 5.2 Sample Field Mapping — Application

| Source Field (legacy) | DDRS Field | Transformation |
| --- | --- | --- |
| file_no / app_no | referenceNo | Preserve or re-key to CDSCO/<TYPE>/<YEAR>/<SEQ> |
| applicant_id | organizationId | Resolve to migrated organization UUID |
| form_type | type | Map to ApplicationType enum |
| status_code | status | Map to ApplicationStatus (DRAFT…ISSUED) |
| submitted_on | submittedAt | Parse to ISO datetime |
| fee_amount | feeAmount | Validate against fee rules |
| product_category | productCategory | Map to ProductCategory enum |
| state | stateCode | Map to 2-letter code |

# 6. Data Quality, Validation & Reconciliation

## 6.1 Data Quality Dimensions

| Dimension | Check |
| --- | --- |
| Completeness | Mandatory fields present; no truncation |
| Accuracy | Values match source / reference data |
| Consistency | Enums, codes and references normalised |
| Uniqueness | No duplicates (entities, products, persons) |
| Integrity | All foreign keys resolve; no orphans |
| Validity | Conforms to DDRS validation rules |

## 6.2 Reconciliation

Per-entity source vs target row counts with variance log.

Checksum/hash comparison for documents.

Business-rule validation (e.g., licence validity, status legality).

Statistical and sample-based manual audits with sign-off.

## 6.3 Acceptance Criteria

100% of in-scope records migrated or formally exception-listed.

Reconciliation variance within agreed tolerance (target 0 for critical data).

No unresolved referential-integrity errors.

CDSCO sign-off per wave before production promotion.

# 7. Cutover, Rollback & Tools

## 7.1 Cutover & Parallel Run

Each wave runs DDRS in parallel with the legacy system for a defined window; delta records are captured and applied; users are switched at cutover with hypercare support.

## 7.2 Rollback

Every load is reversible: staging snapshots and pre-load backups allow a wave to be rolled back without affecting previously migrated, signed-off data.

## 7.3 Tooling

| Concern | Approach |
| --- | --- |
| Extraction | Source DB connectors / API exports / CSV-TSV |
| Staging | Isolated schema with data-quality rules and audit |
| Transform/Load | Scripted ETL into DDRS (TypeORM/SQL), batched |
| Validation | Automated reconciliation reports + dashboards |
| Documents | Object storage with checksum + version capture |

# 8. Governance, RACI, Risks & Schedule

## 8.1 RACI

| Activity | CDSCO | SSP | Source Owner | DBA |
| --- | --- | --- | --- | --- |
| Source access & schemas | A | C | R | C |
| Profiling & mapping | A | R | C | C |
| Cleansing rules | A | R | C | I |
| ETL build & load | I | R | I | C |
| Validation & reconciliation | A | R | C | C |
| Cutover sign-off | A | C | C | I |

## 8.2 Risks & Mitigations

| Risk | Mitigation |
| --- | --- |
| Poor legacy data quality | Early profiling; cleansing rules; exception handling |
| Schema ambiguity | Workshops with system owners; iterative mapping |
| Large document volume (24.3 TB) | Phased document migration; checksum verification |
| Downtime risk | Parallel run + delta capture + scheduled cutover windows |
| Referential gaps | Dependency-ordered loading; orphan resolution |
| Sensitive data exposure | Encryption, access control, masked non-prod data |

## 8.3 Indicative Schedule

| Wave | Scope | Window |
| --- | --- | --- |
| W0 | Assessment, profiling, mapping, tooling | Months 1–2 |
| W1 | Central master + SUGAM/MD core | Months 2–4 |
| W2 | SUGAM LABS + high-volume States (ONDLS) | Months 4–7 |
| W3 | Remaining States/UTs + documents | Months 7–10 |
| W4 | Delta, reconciliation close-out, archive | Months 10–12 |

# Appendix A — Reconciliation Report Template

| Entity | Source count | Target count | Variance | Exceptions | Status |
| --- | --- | --- | --- | --- | --- |
| organizations | — | — | — | — | — |
| products | — | — | — | — | — |
| applications | — | — | — | — | — |
| licenses | — | — | — | — | — |
| samples | — | — | — | — | — |

# Appendix B — Mapping Specification Template

| Source field | Type | DDRS field | Type | Rule | Default |
| --- | --- | --- | --- | --- | --- |
| — | — | — | — | — | — |

— End of Document —